## Biểu đồ Gantt
GANTT CHART
PROJECT NAME |  | CaRe |  |  |  | TEAM NAME |  | jcxdc
PROJECT MANAGER |  | Triệu Nhật Minh |  |  |  | DATE |  | 2023-10-31
Work Breakdown Structure | TASK DESCRIPTION | PEOPLE IN CHARGE (P.I.C.) | START DATE | END DATE | PROGRESS | SPRINT 1 |  |  | SPRINT 2 |  | SPRINT 3 |  | SPRINT 4 |  | SPRINT 5 |  | SPRINT 6
[6 empty] | WEEK 1 (19/10-25/10) | WEEK 2 (26/10-1/11) |  | WEEK 3 (2/11-8/11) | WEEK 4 (9/11-15/11) | WEEK 5 (16/11-22/11) | WEEK 6 (23/11-29/11) | WEEK 7 (30/11-6/12) | WEEK 8 (7/12-13/12) | WEEK 9 (14/12-20/12) | WEEK 10 (21/12-27/12) | WEEK 11 (28/12-3/1) | WEEK 12 (4/1-10/1)
1 | Inception
2023-01-01 | Sprint 1 (PA1) |  | 19/10/23 | 01/11/23
1.1.1 | PA0 submission
1.1.1.1 | Proposal | NMinh
1.1.2 | Software Development plan
1.1.2.1 | Introduction: Purpose, Scope, Overview | DViet |  |  | 100%
1.1.2.2 | Project Overview | AThu |  |  | 100%
1.1.2.3 | Project Organization | NMinh |  |  | 100%
1.1.2.4 | Project Estimates, Plan | NTruc |  |  | 100%
1.1.2.5 | Project Monitoring and Control | DQuan |  |  | 100%
1.1.2.6 | Gantt Chart | NTruc |  |  | 100%
1.1.2.7 | Jira update | NMinh |  |  | 100%
1.1.3 | Vision Document
1.1.3.1 | Positioning | DQuan |  |  | 100%
1.1.3.2 | Stakeholder and User Descriptions | DViet |  |  | 100%
1.1.3.3 | Product Overview | NMinh |  |  | 100%
1.1.3.4 | Product Features | NTruc |  |  | 100%
1.1.3.5 | Non-Functional Requirements | AThu |  |  | 100%
2 | Elaboration
2023-01-02 | Sprint 2 (PA 2)
2.1.1 | Revised project plan, vision document
2.1.2 | Design use-case model by StarUML, Visio and other tool
2.1.3 | Use-case Specifications
2.2 | Sprint 3 (PA 3)
2.2.1 | Revised use-case model
2.2.2 | Revised use-case specification
2.2.3 | Architecture document: Package diagram, Data Access diagram
2.2.4 | Architecture document: Serializer diagram, Model diagram, Data Access diagram
2.2.5 | Architecture document: Presentation diagram
2.2.6 | Architecture document: Presentation diagram, Controller diagram
2.2.7 | Architecture document: Controller diagram
3 | Construction
3.1 | Sprint 4 (PA 4)
3.1.1 | Revised architecture document
3.1.2 | Architecture document: Deployment
3.1.3 | Architecture document: Implementation view
3.1.4 | UI prototypes
3.2 | Sprint 5 (PA 5)
3.2.1 | Revised artifacts submitted in Elaboration
3.2.2 | Test plan
3.2.3 | Test cases
3.3 | Sprint 6 (PA 6)
3.3.1 | Test cases (Fill in 2 remaining fields, actual result, and status (Passed / Failed)) and Test Reports
3.3.2 | Automated testing
3.3.3 | Project presentation
2023-04-03 | Coding
3.4.1 | Back-end
3.4.1.1 | Database design
3.4.2 | Front-end
4 | Trainning
2018-01-04 | Figma
2018-02-04 | Typescript
2023-03-04 | MongoDB
5 | Meeting Reports
5.1 | Sprint 1
5.2 | Sprint 2
5.3 | Sprint 3
5.4 | Sprint 4
5.5 | Sprint 5
5.6 | Sprint 6